## Quote Summary
Colorado Barricade Co.
TRAFFIC CONTROL COST ESTIMATE
Generated | 2026-10-16 11:41
Project: Audit 9 southhigh-r-25
Speed 25 mph ¦ Closure: Shoulder Closure · 2-Lane Undivided ¦ Road: Urban (low-speed)
Work zone: 200 ft ¦ Duration: 1 day(s)
Category | Amount
Equipment Rental | 155.5
Labor | 375
Delivery & Logistics | 300
SUBTOTAL | 830.5
Overhead (10%) | 83.05
Profit (10%) | 91.36
TOTAL ESTIMATE | 1004.91

## Equipment Detail
Item # | Device Type | Label | Description | Qty | Unit | Daily Rate | Days | Extended | Notes
1 | SIGN_GENERIC | G20-1 | G20-1 ROAD CONSTRUCTION (NEXT 200 FT) | 1 | EACH | 4 | 1 | 4
2 | SIGN_GENERIC | G20-2 | G20-2 END ROAD WORK | 1 | EACH | 4 | 1 | 4
3 | SIGN_GENERIC | G20-5P | G20-5P CONSTRUCTION ZONE plaque | 1 | EACH | 4 | 1 | 4
4 | SIGN_GENERIC | R9-9 | R9-9 SIDEWALK CLOSED | 2 | EACH | 4 | 1 | 8
5 | SIGN_GENERIC | W20-1 | W20-1 ROAD WORK AHEAD | 1 | EACH | 4 | 1 | 4
6 | SIGN_GENERIC | W20-2 | W20-2 ROAD WORK 491 FT | 1 | EACH | 4 | 1 | 4
7 | SIGN_GENERIC | W21-5aR | W21-5aR RIGHT SHOULDER CLOSED AHEAD | 1 | EACH | 4 | 1 | 4
8 | DRUM |  | 36-inch channelizing drum with alternating orange/white stripes | 4 | EACH | 3 | 1 | 12
9 | CONE |  | Traffic Cone (28-inch) | 7 | EACH | 1.5 | 1 | 10.5
10 | BARRICADE_TYPE_III |  | Type III barricade: three horizontal striped rails, full lane width | 2 | EACH | 8 | 1 | 16
11 | ARROW_BOARD |  | Trailer-mounted flashing arrow board (Type A, B, or C) | 1 | EACH | 85 | 1 | 85
[7 empty] | SUBTOTAL | 155.5

## Labor Detail
Role | Personnel | Hours/Day | Days | Rate ($/hr) | Extended
Flaggers | 0 | 10 | 1 | 55 | 0
TCS Supervisor | 1 | 2 | 1 | 75 | 150
Setup Crew | 2 | 1.5 | 1 | 45 | 135
Takedown Crew | 2 | 1 | 1 | 45 | 90
|  |  |  | SUBTOTAL | 375
Standard shift: 10 hours including mobilization. Overtime billed at 1.5x after 8 hours per Colorado labor law.

## Delivery & Logistics
Item | Trips | Distance (mi) | Rate ($/mi) | Min Charge | Extended
Equipment Delivery | 2 | 20 | 3.5 | 150 | 300
|  |  |  | SUBTOTAL | 300

## Terms & Conditions
TERMS AND CONDITIONS
1. Prices valid for 30 days from date of estimate.
2. Minimum 4-hour call-out for all labor.
3. Night work (sunset to sunrise) billed at 1.5x standard rate.
4. Equipment rental begins at time of delivery to site.
5. Setup and takedown charged per occurrence.
6. Damaged or missing equipment billed at replacement cost.
7. Traffic control plan (MHT) included with this estimate.
8. All work performed by ATSSA/CCA-certified personnel.
9. This estimate is for planning purposes only. Final pricing subject to site inspection and contract terms.
Generated by Conestruct · conestruct.com